## Product_Backlog
Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Status
Sprint 1 | US-001 | As a user, I want to submit an issue using free-text input so that I can report problems easily without filling complex forms | MUST | None | Completed
Sprint 1 | US-002 | As a system, I want to preprocess user input text to remove noise and normalize data for accurate analysis | MUST | US-001 | Completed
Sprint 1 | US-003 | As a system, I want to label and annotate ticket data so that it can be used to train NLP models | MUST | US-002 | Completed
Sprint 2 | US-004 | As a system, I want to classify tickets into categories like hardware or software issues automatically | SHOULD | US-003 | Completed
Sprint 2 | US-005 | As a system, I want to extract entities such as usernames, error codes, ana services using NEP | SHOULD | US-003 | Completed
Sprint 3 | US-006 | As a system, I want to determine ticket priority based on intent and sentiment analysis | COULD | US-004,US- 005 | Completed
Sprint 3 | US-007 | As a system, I want to generate a structured ticket with title, description, category, and priority | MUST | US-006 | Completed
Sprint 4 | US-008 | As a user, I want to view the generated ticket details before submission for confirmation | SHOULD | US-007 | Completed
Sprint 4 | US-009 | As an admin, I want the system to log all created tickets for reporting and analysis | COULD | US-008 | Completed
Sprint 4 | US-010 | As a system, I want to provide basic analytics on ticket categories and priorities | WON'T | US-009 | Pending

## Sprint_Backlog
Sprint | User Story ID | User Story / Task | Module | Priority | Status | Assigned To | Notes
Sprint 1 | US-01 | Collect diverse dataset of past user issues | Module 1: Data Collection & Preprocessing | High | Done | Data Team | Historical ticket data
Sprint 1 | US-02 | Clean and preprocess text data | Module 1: Data Collection & Preprocessing | High | Done | Data Team | Handle inconsistencies, spelling errors
Sprint 1 | US-03 | Annotate dataset with labels for categories, priorities, entities | Module 1: Data Collection & Preprocessing | High | Done | Data Team | Manual annotation
Sprint 2 | US-04 | Develop and train NLP model for text classification | Module 2: NLP Model Development | High | Done | ML Team | scikit-learn classifiers
Sprint 2 | US-05 | Implement Named Entity Recognition (NER) | Module 2: NLP Model Development | High | Done | ML Team | SpaCy for NER
Sprint 2 | US-06 | Fine-tune model for intent and sentiment analysis | Module 2: NLP Model Development | Medium | Done | ML Team | Priority assignment
Sprint 3 | US-07 | Build core ticket generation engine | Module 3: Ticket Generation Engine | High | Done | Backend Team | JSON output
Sprint 3 | US-08 | Map extracted entities to ticket fields | Module 3: Ticket Generation Engine | High | Done | Backend Team | title, description, category, priority
Sprint 4 | US-09 | Develop web-based user interface (chatbot/form) | Module 4: UI & Integration Layer | Medium | Done | Frontend Team
Sprint 4 | US-10 | Integrate AI engine with UI for real-time processing | Module 4: UI & Integration Layer | High | Done | Full Stack Team
Sprint 4 | US-11 | Create ticket confirmation display for users | Module 4: UI & Integration Layer | Medium | Done | Frontend Team

## Stand_up_Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Dataset collection - limited access to historical ticket logs | Requested access from IT; used sample public helpdesk datasets
Sprint 1 | Day 1 | Inconsistent data formats across ticket sources | Wrote normalization script to standardize CSV formats
Sprint 1 | Day 2 | Annotation tool setup delays | Used Label Studio as annotation tool; setup completed
Sprint 1 | Day 2 | Team disagreement on label categories | Held category definition meeting; finalized 5 ticket categories
Sprint 1 | Day 3 | Annotation quality inconsistency among team members | Created annotation guidelines document; inter-annotator review
Sprint 2 | Day 3 | Model selection uncertainty (BERT vs scikit-learn) | Decided on scikit-learn for speed; BERT as future upgrade
Sprint 2 | Day 4 | Low initial model accuracy (~62%) | Added more training data; tuned hyperparameters
Sprint 2 | Day 4 | Overfitting on training data | Applied cross-validation and regularization techniques
Sprint 2 | Day 5 | Sentiment model not distinguishing urgency well | Added urgency keywords as features to the model
Sprint 3 | Day 5 | JSON schema not finalized for ticket output | Defined schema: title, description, category, priority, entities
Sprint 3 | Day 6 | Priority assignment logic too simplistic | Enhanced logic with keyword weights and sentiment score
Sprint 3 | Day 6 | Environmental Setup Testing | Testing Database
Sprint 4 | Day 7 | Deployment Configuration | Set up deployment scripts
Sprint 4 | Day 7 | Real-time processing latency issues | Optimized model loading; moved to in-memory model caching

## Retrospective
Sprint | What Went Well | What Could Be Improved | Action Items for Next Sprint
Sprint 1 | Successfully collected and cleaned diverse dataset; team collaboration was strong during annotation | Annotation process took longer than estimated; category definitions should have been finalized earlier | Finalize all label definitions before next sprint; automate data validation checks
Sprint 2 | NLP model reached acceptable accuracy (78%); NER extracted most entities correctly | Overfitting issue delayed milestone; more training data needed earlier | Expand training dataset; implement automated model evaluation pipeline
Sprint 3 | Ticket generation engine produces well-structured JSON; end-to-end flow tested successfully | Priority logic still has edge cases; integration debugging took extra time | Add unit tests for ticket engine; refine priority scoring algorithm
Sprint 4 | Web UI deployed successfully; real-time ticket generation working; user confirmation screen functional | Latency optimization was reactive, not proactive; documentation was incomplete during development | Write final project report; add performance benchmarks; document API endpoints